Detailed Mitigation Plan for Risk TEC-01: Simulation-Physical Mismatch

Risk ID: TEC-01 Risk Name: Simulation-Physical Performance Mismatch Risk Description: The risk that the physically fabricated PBA material prototypes fail to achieve the performance targets (e.g., energy density, conductivity, cycle life) predicted by the quantum simulation models and the AI-Design of Experiments (AI-DOE) framework. Potential Impact (per PBA_Optimization_Cost_Analysis.md):

- Schedule: 12-18 month delay to market.

- Cost: $15-25M in additional, unplanned R&D costs to re-run simulations and fabrication cycles.

- Performance: Failure to meet the Go/No-Go criteria, potentially requiring a project pivot or termination.

Mitigation Strategy & Action Plan

The mitigation strategy is divided into three phases: Proactive (preventing the mismatch), Reactive (correcting the mismatch when detected), and Contingent (actions to take if the mismatch cannot be resolved).

Phase 1: Proactive Mitigation (Tasks 1 & 2)

These actions are designed to minimize the probability of a mismatch before any significant fabrication resources are committed.

| Action Item | Description | Trigger / Timing | Responsible Team | Success Metric |
| --- | --- | --- | --- | --- |
| 1.1: Model Anchoring & Baseline Validation | Before simulating novel PBA compositions, the quantum physics models (DFT, CWF via Psi4, CP2K) will be run on well-characterized baseline materials (e.g., standard Fe4[Fe(CN)6]3). The simulation output will be compared against established experimental data for these materials. | Task 1 (Weeks 1-4) | Quantum Modeling Team | T1 Exit Criteria: Model achieves R² ≥ 0.85 correlation between predicted and known physical properties for baseline materials. |
| 1.2: Implement Physics-Informed Constraints | The AI-DOE framework will be constrained with known physical and chemical rules. This includes setting limits on dopant concentrations to avoid phase instability and enforcing manufacturability constraints (e.g., deposition temperatures) to prevent the AI from exploring physically impossible designs. | Task 2 (Weeks 9-10) | AI/ML Team | The AI model's surrogate g(x)≥0 phase-stability classifier correctly identifies >95% of known unstable compositions. |
| 1.3: Maintain a Diverse Candidate Portfolio | Instead of selecting a single "best" design from the AI-DOE, the top 10 candidate compositions will be selected based on a Pareto frontier analysis. This portfolio will balance predicted performance against manufacturability risk and material cost. | Task 2 (Weeks 15-16) | Project Lead, Modeling & Fab Teams | T2 Exit Criteria: A short-list of 10+ designs is generated, each meeting the μ/σ ≥ 3 uncertainty threshold and a manufacturability score ≥0.7. |

Phase 2: Reactive Mitigation (Task 3)

These actions are triggered during the initial prototyping phase to rapidly correct any observed deviations.

| Action Item | Description | Trigger / Timing | Responsible Team | Success Metric |
| --- | --- | --- | --- | --- |
| 2.1: Staggered Prototyping & Rapid Feedback | Instead of fabricating all 10 candidate designs at once, fabrication will be staggered. The top 3 candidates will be fabricated first. Structural (XRD) and electrical (EIS) data from these initial prototypes will be immediately fed back to the modeling team. | Task 3 (Weeks 17-24) | Fabrication Team, Test & Validation Team | Initial physical data is available for model re-evaluation within 6 weeks of starting Task 3. |
| 2.2: Bayesian DOE Reweighting | If a mismatch is detected (e.g., prototype performance is >20% off from prediction), the AI-DOE model will be updated using the new physical data points. The Bayesian optimization algorithm will re-weight the parameter space, deprioritizing regions that led to poor results and prioritizing new regions informed by the physical data. | Triggered by results from Action 2.1 | AI/ML Team, Quantum Modeling Team | The updated model's prediction error for the initial prototypes is reduced by >50%. |
| 2.3: Prioritize Next Fabrication Batch | Based on the re-weighted DOE, a new set of 3-5 candidates will be selected from the remaining portfolio or newly generated simulations for the next fabrication run. | Following completion of Action 2.2 | Project Lead, Fabrication Team | The second batch of prototypes demonstrates performance within 20% of the updated predictions. |

Phase 3: Contingency Plan

This plan is enacted if the mismatch proves persistent and cannot be resolved through iterative re-weighting.

| Action Item | Description | Trigger / Timing | Responsible Team | Success Metric |
| --- | --- | --- | --- | --- |
| 3.1: Root Cause Analysis (RCA) Task Force | A dedicated task force of modeling, fabrication, and testing experts will be formed to conduct a deep-dive RCA. This includes forensic analysis of failed prototypes (TEM, SIMS) and a full audit of the simulation environment and fabrication process logs. | If two consecutive fabrication batches fail to meet the T3 Exit Criteria. | CTO, Project Lead, Team Leads | A formal RCA report identifying the primary source of the mismatch (e.g., an unmodeled physical effect, a process contamination issue) is delivered within 4 weeks. |
| 3.2: Pivot to Backup Formulations | The project will pivot to fabricating "backup" formulations. These are lower-risk, less aggressive designs identified during the initial AI-DOE that may have lower predicted performance but a much higher probability of manufacturability and stability. | Following the RCA report if the primary path is deemed unrecoverable. | Project Lead, Fabrication Team | A backup formulation successfully passes the T3 Exit Criteria, providing a viable, albeit potentially lower-performance, path to a licensable product. |
| 3.3: Re-scope Project & Re-baseline | If the core PBA approach is deemed fundamentally flawed, the project's scope, budget, and timeline will be formally re-baselined. This may involve shifting focus to an entirely different material class (e.g., layered oxides) while leveraging the validated aspects of the AI-DOE framework. | If both primary and backup formulations fail. | Executive Leadership, Project Lead | A revised project charter with new technical targets, a new budget, and a new schedule is approved by stakeholders. |