Risk Register for PBA Alternative Project

Here is a risk register for the Prussian Blue Analog (PBA) alternative project, generated in markdown format. The probabilities and impacts are taken directly from the probabilistic data in the MASTER_VALIDATION_DATABASE.txt and Q-SMEC Deep Scientific Analysis_text.txt files.

| Risk ID | Risk Description | Category | Probability (P) | Impact (I) | Expected Loss (P × I) | Mitigation Strategy |
| --- | --- | --- | --- | --- | --- | --- |
| TEC-01 | Simulation-Physical Mismatch: The performance of the fabricated PBA prototype (e.g., energy density, cycle life) does not match the predictions from the quantum models and AI-DOE simulations. | Technical | 35% | $400,000 | $140,000 | 1. Anchor quantum models with early physical test data from baseline materials. 2. Use Bayesian optimization to re-weight the DOE parameter space based on initial prototype results. 3. Maintain a diverse portfolio of the top 10 candidate compositions for fabrication. |
| MAN-01 | Fabrication Yield Shortfall: The manufacturing process (CVD, annealing) for the PBA material fails to achieve the required yield (T3 Exit: ≥60%, T5 Exit: ≥80%) or quality metrics (e.g., XRD FWHM, stoichiometry). | Technical / Manufacturing | 30% | $300,000 | $90,000 | 1. Implement Statistical Process Control (SPC) on key process parameters (temperature, pressure, time). 2. Establish inline metrology gates (e.g., post-deposition XRD) to catch deviations early. 3. Develop and validate "golden" tool recipes and retain twin samples for forensic analysis. |
| SUP-01 | Supply Chain Constraints: Delays or quality issues in procuring high-purity precursor materials (e.g., iron salts, cyanides, dopant sources) for the PBA synthesis. | Business / Supply Chain | 25% | $200,000 | $50,000 | 1. Qualify and establish relationships with at least two independent suppliers for critical precursors. 2. Maintain a strategic buffer inventory of long-lead-time or single-source materials. 3. Implement incoming quality control (IQC) to verify purity of all raw materials. |
| FUN-01 | Under-Capitalized Prototypes: Insufficient funding to complete the full 54-week NRE cycle, potentially halting the project after initial modeling (Task 1-2) but before a licensable prototype (Task 4) is ready. | Funding | - | High | - | 1. Utilize the partner co-IP funding model where a strategic partner funds development in exchange for IP rights. 2. Structure funding tranches tied to the successful completion of TRL Go/No-Go gates. |
| IP-01 | Leakage of Confidential Material: Unauthorized disclosure of the proprietary PBA composition (e.g., the specific dopants used from the 12 undisclosed elements) or manufacturing processes. | IP / Security | - | High | - | 1. Enforce strict NDAs with all personnel and partners. 2. Operate within a secure data enclave with access controls. 3. Use a partial disclosure strategy, revealing only necessary information to partners at each stage. |