TRL Development Plan Comparison: PBA vs. Terahertz Sensor

Based on the documentation, the high-level Non-Recurring Engineering (NRE) plan is standardized for every Q-SMEC instantiation. Both the Prussian Blue Analog (PBA) battery alternative and the Terahertz (THz) sensor would follow the same six-task, 54-week, $770,000 development program.

The key differences lie not in the structure of the plan, but in the specific scientific focus, prototype design, and validation metrics within each task.

| NRE Task (Duration, Cost) | Prussian Blue Analog (PBA) Alternative | Terahertz (THz) Sensor |
| --- | --- | --- |
| Task 1: Quantum Modeling(8 weeks, $100K) | Focus: Modeling ionic diffusion, intercalation chemistry, electronic conductivity, and lattice strain in the PBA framework.KPIs: Energy density (Wh/L, Wh/kg), internal resistance (ESR), and structural stability. | Focus: Modeling electromagnetic field interactions, plasmonics, electron-photon coupling, and material response at THz frequencies.KPIs: Responsivity (R), Noise-Equivalent Power (NEP), and Detectivity (D*). |
| Task 2: AI-DOE(8 weeks, $110K) | Optimization Goal: Maximize energy density and cycle life while minimizing internal resistance. The 6,561 simulations will explore compositions that enhance ion transport and reduce strain. | Optimization Goal: Maximize sensitivity (D*) and Signal-to-Noise Ratio (SNR) while minimizing noise (NEP). The simulations will explore compositions with optimal dielectric/magnetic loss at THz frequencies. |
| Task 3: Prototype Fabrication(12 weeks, $190K) | Prototype Form Factor: 2032 coin-cell test vehicles. This involves coating SMEC materials onto positive/negative electrodes (5-20 μm layers) and assembling them into a battery cell. | Prototype Form Factor: 2x2 mm EM sensor die. This involves fabricating micro-scale structures like interdigitated electrodes and potentially flux concentrators or backside reflectors. |
| Task 4: Manufacturability Beta(10 weeks, $110K) | Process Validation: Validating thin-film deposition (CVD/PVD) uniformity over electrode surfaces and ensuring consistent electrochemical properties in small batches. | Process Validation: Validating nano-imprint lithography or additive patterning for creating precise sensor geometries with high yield and low critical dimension (CD) variance. |
| Task 5: Pre-Production(8 weeks, $130K) | Test & Validation: Galvanostatic charge/discharge cycling (C/10 to 5C), Electrochemical Impedance Spectroscopy (EIS), and cycle life testing to 80% State of Health (SoH). | Test & Validation: Characterizing responsivity with a monochromator, measuring noise power spectral density (PSD), and calculating NEP and D* in a calibrated RF/optical test environment. |
| Task 6: Final Device Integration(8 weeks, $130K) | Integration: Integrating the optimized coin cells into a representative battery pack or module with a Battery Management System (BMS) for a system-level demonstration. | Integration: Integrating the sensor die into a complete front-end module with a low-noise amplifier (LNA), control electronics, and housing for an operational demonstration. |

In summary, while the project management framework is identical, the underlying scientific and engineering work is highly specialized. The PBA path is rooted in electrochemistry and materials science, while the THz sensor path is rooted in electromagnetics and semiconductor physics.