# P248 Schedule & Prime Partners — Personal War-Fighter System

Date: January 12, 2026
Scope: Personal foam fractionation purifier (1–10 GPD); Tucson-first execution with Arizona secondary options

## P248 Test Schedule (Personal System) — Tucson First

| Test Focus | Primary Lab/Location | Target Window | Owner | Status |
| --- | --- | --- | --- | --- |
| Biological efficacy (P248) | Tucson, AZ (primary water lab partner) | Feb 3–7, 2026 | QA Lead | Scheduled |
| Chemical removal panel (industrial/chemical agents) | Tucson, AZ | Feb 10–14, 2026 | QA Lead | Scheduled |
| Turbidity/particulate + flow endurance (fresh + salt) | Tucson, AZ | Feb 17–21, 2026 | Systems Eng | Scheduled |
| Thermal extremes (MIL-STD-810H profiles) | Tucson, AZ | Feb 24–26, 2026 | Test Eng | Pending confirmation |
| Shock/vibration (MIL-STD-810H) | Phoenix, AZ (secondary) | Mar 3–4, 2026 | Test Eng | Pending slot |
| Sand/dust ingress | Yuma Proving Ground, AZ (secondary) | Mar 10–12, 2026 | Test Eng | Tentative |
| Documentation & reporting package | Tucson, AZ | Mar 17–21, 2026 | QA Lead | Planned |

Notes: Prioritize Tucson labs first; Phoenix/Yuma are secondary fallbacks. Coordinate logistics to keep all fixtures and cartridges staged in Tucson.

## Lab Contacts / Points of Contact (POCs)

| Lab / Function | Location | Primary POC | Role/Notes | Contact |
| --- | --- | --- | --- | --- |
| Turner Laboratories Inc. (P248 bio/chem panels) | 2445 North Coyote Drive, Suite 104, Tucson, AZ 85745 | Elizabeth Kasik | Laboratory Director; schedules P248 bio/chem panels | Phone: 520-882-5880; frontdesk@turnerlabs.com |
| Yuma Proving Ground (sand/dust, military environmental) | Yuma Proving Ground, AZ 85365 | Col. John Nelson | Commander; coordinates YPG test support | Phone: 928-328-2163; Public Affairs Office |
| Yuma Proving Ground (technical oversight) | Yuma Proving Ground, AZ 85365 | Mr. Ross Gwynn | Technical Director; technical oversight and coordination | Phone: 928-328-2163; Public Affairs Office |

Action: reconfirm dates with Turner Labs (Kasik) and YPG (Nelson/Gwynn) by Jan 19, 2026; keep single logistics hub in Tucson for fixtures/cartridges.

## Prime Partner Contact Targets (Tucson Priority)

- Priority geography: Tucson, Arizona (primary); rest of Arizona (secondary).

- Objective: Secure teaming for LRIP/FRP channels, certification support, and soldier-systems integration.

| Organization | Location | Channel/Program | Primary Contact Method | Notes |
| --- | --- | --- | --- | --- |
| RTX (Raytheon) | 1151 E Hermans Rd, Tucson, AZ 85756 | Soldier systems / missile sustainment | Via RTX Careers/Partnerships Portal | Missile systems hub; request intro via Tucson BD team |
| Collins Aerospace (RTX) | 3414 S 5th St, Ste 1, Phoenix, AZ 85040 | Soldier power/avionics tie-ins | Phone: 480-857-xxxx (main); Collins Customer Support: +1-877-808-7575 | Share power envelope + QSMEC API summary via customer support |
| General Dynamics Mission Systems | Scottsdale, AZ campus | Soldier systems integration / OTA | Small Business Liaison Officer: Stephanie Poppe (Scottsdale); Supplier Portal | Register as supplier; focus on OTA/edge security alignment |
| L3Harris Technologies | Phoenix/Tucson, AZ | Soldier comms/systems | General inquiries: via L3Harris Careers/Contact Portal; AZ Jobs page available | Schedule capability brief with demo kit + telemetry |
| Local AZ manufacturing (Berry-compliant) | Tucson area | Enclosure/harness/Berry compliance | Research candidates: Fusion Tactical USA, Keder Solutions, SX Defense, K&T Textiles | Price BOM + Berry-compliant harness options; prioritize Tucson-local if available |

Action: Reach out to Collins Customer Support and GDMS Small Business Liaison (Stephanie Poppe) by Jan 20, 2026; register with GDMS Supplier Portal; request Tucson BD intros for RTX/L3Harris via existing contacts or local chambers.