## Dashboard
Metric | Value | Target | Status
Tool Adoption Rate | 28.21% | 80% | 🔴 Low
Integration Completeness | 75.0% | 60% | 🟢 High
Q-SMEC Readiness | 26.67% | 75% | 🔴 Low
Superconducting Setup | 40.0% | 80% | 🔴 Low
Quantum Sensors | 0.0% | 70% | 🔴 Low
AI Models | 40.0% | 80% | 🔴 Low
Total Tools in Database | 39 | -
Installed Tools | 11 | -
Identified Integration Pairs | 4 | -
Implemented Integrations | 3 | -

## Installed Tools
Tool | Status | Category
qiskit | ✅ Installed | Quantum
cirq | ✅ Installed | Quantum
pennylane | ✅ Installed | Quantum
tensorflow | ✅ Installed | AI/ML
pytorch | ✅ Installed | AI/ML
keras | ✅ Installed | AI/ML
scikit-learn | ✅ Installed | AI/ML
numpy | ✅ Installed | AI/ML
scipy | ✅ Installed | AI/ML
matplotlib | ✅ Installed | AI/ML
jupyter | ✅ Installed | AI/ML

## Integrations
Integration | Status | Priority
Vqe Simulation | ✅ Implemented | Medium
Qaoa Optimization | ✅ Implemented | Medium
Quantum Circuits | ✅ Implemented | Medium
Tensorflow Qiskit | ⏳ Pending | Medium
Pytorch Cirq | ⏳ Pending | Medium
Airth Sensor | ⏳ Pending | Medium
Q-Smec Superconducting | ⏳ Pending | High
Q-Smec Quantum Sensors | ⏳ Pending | High
Master Platform | ⏳ Pending | High

## Q-SMEC Components
Category | Component | Status
Superconducting | Josephson Junction Model | ⏳ Pending
Superconducting | Squid Simulation | ⏳ Pending
Superconducting | Low Temp Physics | ⏳ Pending
Superconducting | Superconducting Qubits | ✅ Complete
Superconducting | Quantum Circuits | ✅ Complete
Quantum Sensors | Magnetic Field Detection | ⏳ Pending
Quantum Sensors | Squid Array | ⏳ Pending
Quantum Sensors | Quantum Metrology | ⏳ Pending
Quantum Sensors | Sensor Calibration | ⏳ Pending
Quantum Sensors | Airth Integration | ⏳ Pending
Ai Models | Tensorflow Installed | ✅ Complete
Ai Models | Pytorch Installed | ✅ Complete
Ai Models | Trained Classifier | ⏳ Pending
Ai Models | Hybrid Quantum Ai | ⏳ Pending
Ai Models | Mining Detector | ⏳ Pending

## Task Timeline
Task ID | Task | Status | Priority
1 | Install Core Quantum AI Stack | ✅ Complete | Critical
2 | Review High-Value Integration Files | ✅ Complete | Critical
3 | Set Up Q-SMEC Development Environment | ✅ Complete | Critical
4 | Build Quantum Simulation Pipeline | ✅ Complete | High
5 | Integrate AI Tools with Quantum Workflows | ⏳ In Progress | High
6 | AIRTH Mining Sensor Integration | ⏳ Pending | High
7 | Consolidate Duplicate Data | ⏳ Pending | Medium
8 | Expand Database Coverage | ⏳ Pending | Medium
9 | Create Integration Testing Framework | ⏳ Pending | High
10 | Develop Q-SMEC Sensor Integration | ⏳ Pending | High
11 | Create Master Q-SMEC Simulation Platform | ⏳ Pending | Critical
12 | Optimize Database Performance | ⏳ Pending | Medium
13 | Leverage NIKET CII Sector Mappings | ⏳ Pending | High
14 | Fix Database Path Consistency | ⏳ Pending | Medium
15 | Add Relationship Mining | ⏳ Pending | Medium
16 | Create Automated Refresh Workflow | ⏳ Pending | Medium
17 | Extract Install Instructions | ⏳ Pending | Low
18 | Build Tutorial Pipeline | ⏳ Pending | Medium
19 | Consolidate Q-SMEC Knowledge Base | ⏳ Pending | Medium
20 | Master ALL Frameworks | ⏳ Pending | Medium
21 | Learn Quantum Algorithms | ⏳ Pending | Medium
22 | Track Progress Metrics | ✅ Complete | High